## Slide 1: RESPONSIBILITIES FOR PO FUNCTIONS

## Slide 2: SAMPLE: RESPONSIBILITY MATRIX

## Slide 3: Road map to setting up PMO

## Slide 4: NUMBER OF PM NEEDED

## Slide 5: COST OF A PROJECT OFFICE

## Slide 6: COST OF A PROJECT OFFICE

## Slide 7: PROJECT MANAGEMENT TOOLS

## Slide 8: STANDARDS AND METRICS

## Slide 9: PROJECT KNOWLEDGE MANAGEMENT

## Slide 10: Organizational Governance
Strategic Planning
Management of Operation
Portfolio Management
Program Management
Project Management
Processes Tools Metrics
Management by Projects

## Slide 11: Organizational Context of Portfolio Management
Vision
Mission
Organizational Strategy and Objectives
High-Level Operations Planning and Management
Project Portfolio Planning and Management
Management of On-Going Operations
Management of Authorized Programs and Projects

## Slide 12: PROJECT GOVERNANCE

## Slide 13: ORGANIZATION AND STRUCTURE

## Slide 14: FACILITIES AND EQUIPMENT SUPPORT

## Slide 15: RESOURCE MANAGEMENT

## Slide 16: PROJECT PLANNING

## Slide 17: PROJECT AUDITING

## Slide 18: ASSESSMENT

## Slide 19: Cash Flow
Activity | PV | 1 | 2 |  | 3 | 4
A | 50,000 |  |  |  |  | 
B | 40,000 |  |  |  |  | 
C | 60,000 |  |  |  |  | 
D | 30,000 |  |  |  |  | 
Monthly Indirect Cost |  | 5,000 | 5,000 |  | 5,000 | 5,000

## Slide 20: Cash Flow
A | 50,000 |  |  |  |  | 
B | 40,000 |  |  |  |  | 
C | 60,000 |  |  |  |  | 
D | 30,000 |  |  |  |  | 
Monthly Direct Cost |  | 25,000 | 65,000 |  | 75,000 | 15,000
Monthly Indirect Cost |  | 5,000 | 5,000 |  | 5,000 | 5,000
Total Monthly Cost |  | 30,000 | 70,000 |  | 80,000 | 20,000
Cumulative Monthly Cost |  | 30,000 | 100,000 |  | 180,000 | 200,000

## Slide 21: Cash Flow
A | 50,000 |  |  |  |  | 
B | 40,000 |  |  |  |  | 
C | 60,000 |  |  |  |  | 
D | 30,000 |  |  |  |  | 
Monthly Direct Cost |  | 25,000 | 65,000 |  | 75,000 | 15,000
Monthly Indirect Cost |  | 5,000 | 5,000 |  | 5,000 | 5,000
Total Monthly Cost |  | 30,000 | 70,000 |  | 80,000 | 20,000
Cumulative Monthly Cost |  | 30,000 | 100,000 |  | 180,000 | 200,000
Chart: 
| 0 | 1 | 2 | 3 | 4
 | 0 | 30000 | 100000 | 180000 | 200000

## Slide 22: 2-month progress
Activity | PV | 1 | 2 |  | 3 | 4 | % Complete | AC
A | 50,000 |  |  |  |  |  | 100 | 55,000
B | 40,000 |  |  |  |  |  | 60 | 28,000
C | 60,000 |  |  |  |  |  | 40 | 22,000
D | 30,000 |  |  |  |  |  | 10 | 4,000
Monthly Indirect Cost |  | 5,000 | 5,000 |  | 5,000 | 5,000 |  | 10,000
 |  |  |  |  |  |  |  | 119,000

## Slide 23: Cash Flow
Activity | PV | 1 | 2 |  | 3 | 4 | % Complete | EV
A | 50,000 |  |  |  |  |  | 100 | 50,000
B | 40,000 |  |  |  |  |  | 60 | 24,000
C | 60,000 |  |  |  |  |  | 40 | 24,000
D | 30,000 |  |  |  |  |  | 10 | 3,000
Direct EV |  |  |  |  |  |  |  | 101,000
Total EV |  |  |  |  |  |  |  | 112,222

## Slide 24: Performance Report
PV =100,000
EV= 112,222
AC=119,000
SV = 112,222 – 100,000 = 12,222
SPI = 112,222 /100,000 = 1.12
CV = 112,222 – 119,000 = -6,778
CPI = 112,222 /119,000=0.943

## Slide 25: PROJECT PORTFOLIO MANAGEMENT

## Slide 26: PROJECT ATTRITION

## Slide 27: CUSTOMER RELATIONSHIP MANAGEMENT ACTIVITIES

## Slide 28: CUSTOMER RELATIONSHIP MANAGEMENT

## Slide 29: Project Performance
Chart: 
| Criteria 1 | Criteria 2 | Criteria 3 | Criteria 4 | Criteria 5 | Criteria 6
Target | 26 | 35 | 43 | 18 | 9 | 29
Project XYZ | 24 | 27 | 39 | 18 | 8 | 34

## Slide 30: PERFORMANCE VARIANCE

## Slide 31: BENEFITS REALIZATION

## Slide 32: SCORING COMPONENT PERFORMANCE

## Slide 33: CHANGES IN THE WEIGHTING FOR SCORING PERFORMANCE

## Slide 34: PORTFOLIO EFFICIENT FRONTIER

## Slide 35: OUTCOME PROBABILITY ANALYSIS

## Slide 36: Business Performance Management

## Slide 37: PMO Implementation
  Perform General Services
  Report Activities
  Implement and evaluate Methodology
  Promote Standards
  Improve Processes
  Support Software
  Update Plans
  Maintain Knowledge Base

## Slide 38: Communication Model
Ideas, facts, suggestions
Ideas, facts, suggestions
Encode
Decode
Noise
Feedback

## Slide 39: Communication Directions
Upward channel
  Communicate to senior executives
Highlight issues, risks, and exceptions
Status reports, exception reports, charter, reviews, communication plan
  Provide direction to team
Highlight task pending, scheduled tasks, dates, team briefing
Verbal , agendas, minutes, e-mail, briefs, plans, issue logs
Delegation skills
Downward channel
Lateral channel
  Communicate to client, vendors, functional managers
Negotiation for resources, budgets, time
Communication plan, SOW, contracts, e-mail
Diplomacy and tact

## Slide 40: PORTFOLIO COMMUNICATION MANAGEMENT

## Slide 41: COMMUNICATION STRATEGY MATRIX

## Slide 42: STAKEHOLDER MATRIX

## Slide 43: COMMUNICATION MATRIX

## Slide 44: DASHBOARD

## Slide 45
Risk Responsibility Chart |  |  |  | 
 | Top management | PM | Management Team | Risk Owner
Plan Risk Management | X | X | X | 
Identify Risk |  | X | X | 
Perform Qualitative Risk Management |  | X | X | X
Perform Qualitative Risk Management |  | X | X | X
Plan Risk Responses |  | X | X | X
Monitor & Control Risks |  | X | X | X

## Slide 46: Risk Breakdown Structure (RBS)
Project
Organizational
Project
Management
Technical
External
Others
Time
Cost
Resource
Quality
Performance
Complexity
Objectives
Fund
Collaboration
Weather
Labor
Politics

## Slide 47: PORTFOLIO RISK CATEGORIZATION

## Slide 48: Likelihood Expectations
Level | Likelihood | Expected or actual frequency experienced
1 | Rare | May only occur in exceptional circumstances; simple process; no previous incidence of non-compliance
2 | Unlikely | Could occur at some time; less than 25% chance of occurring; noncomplex process &/or existence of checks and balances
3 | Possible | Might occur at some time; 25 –50% chance of occurring; previous audits/reports indicate non-compliance; complex process with extensive checks & balances; impacting factors outside control of organization
4 | Likely | Will probably occur in most circumstances; 50-75% chance of occurring; complex process with some checks & balances; impacting factors outside control of organization
5 | Almost certain | Can be expected to occur in most circumstances; more than 75% chance of occurring; complex process with minimal checks & balances; impacting factors outside control of organization

## Slide 49: Impact Scale
 | Relative or numerical scales |  |  |  | 
Objective | Very low / 0.05 | Low / 0.10 | Moderate / 0.20 | High / 0.40 | Very High / 0.80
Cost | Insignificant increase | <10% increase | 10-20% increase | 20-40% increase | >40% increase
Time | Insignificant increase | <5% increase | 5-10% increase | 10-20% increase | >20% increase
Scope | Barely noticed change | Minor change | Major change | Unacceptable by sponsor | Product is useless
Quality | Barely noticed | Applications affected | Sponsor approval required | Unacceptable by sponsor | Product is useless

## Slide 50
Stakeholder Tolerance Matrix |  |  |  |  | 
Stakeholder | Requirements | Tolerances |  |  | 
 |  | Time | Cost | Quality | 
PM | Deliver product as requested | More than 10% Phase II | More than 5% Phase II | Conformance to all specs | 
Technical Manager | Passing all QC criteria | More than 20% Phase II | More than 10% Phase II | Conformance to all limitations | 
Marketing Manager | Verify profits | More than 5% Phase II | More than 2% Phase II | Customer acceptance | 
IT Manager | Customer satisfaction (internal & external) | More than 20% Phase II | More than 5% Phase II | Positive feedback | 

## Slide 51: Risk Matrix
 | Consequences |  |  |  | 
Likelihood | Insignificant | Minor | Moderate | Major | Extreme
Rare | Low | Low | Low | Low | Low
Unlikely | Low | Low | Low | Medium | Medium
Possible | Low | Low | Medium | Medium | Medium
Likely | Low | Medium | Medium | High | High
Almost certain | Low | Medium | Medium | High | Extreme

## Slide 52: Cause & Effect
Delay in Project
Management
Materials
Funding
Scope
Productivity
Labor

## Slide 53: SWOT
 | PRO | CON
Internal | Strength | Weakness
External | Opportunity | Threat

## Slide 54: Risk Register
Task | Cause | Risk | Effect
Design | Conflict | Errors + Rework | Delay
Procurement | Single supplier | Inappropriate delivery | Delay / cost increase
Handing out | Permit not ready | No access | Delay
Executing | Technical problems | Rework | Delay / Cost increase
Verification | Nonconformance | Corrective action | Quality / Cost/ Time

## Slide 55: Probability – Impact Matrix
Impact | 0.9 | 0.7 | 0.5 | 0.3 | 0.1
Probability |  |  |  |  | 
0.9 | 0.81 | 0.63 | 0.45 | 0.27 | 0.09
0.7 | 0.63 | 0.49 | 0.35 | 0.21 | 0.07
0.5 | 0.45 | 0.35 | 0.25 | 0.15 | 0.05
0.3 | 0.27 | 0.21 | 0.15 | 0.09 | 0.03
0.1 | 0.09 | 0.07 | 0.05 | 0.03 | 0.01

## Slide 56: PROBABILITY – IMPACT MATRIX

## Slide 57: Probability – Impact Chart
High impact
High probability
Low probability
Low impact

## Slide 58: Critical Events
High urgency
Low urgency
High severity
Low severity

## Slide 60: SENSITIVITY ANALYSIS
Inflation
Currency
Discount rate
Market demand
Conformance
-$2M
-$1M
$0M
+$1M
+$2M
Tornado Diagram