## Slide 1: إدارة المشروعات Projects Management
د. باسم ممدوح الحلوانى
Lecture 7
Time Management
Part 3

## Slide 2
P5: Developing the Schedule
Practical Considerations for Developing the Schedule
Calendar Dates
Use Network Information
Extended Network Techniques to Come Close to Reality
Avoid Dangler Paths
Dummy tasks

## Slide 3
P5: Developing the Schedule
Practical Considerations for Developing the Schedule
Calendar Dates
Week end days and
National and International holidays must be considered carefully

## Slide 4
Practical Considerations for Developing the Schedule
Network Information
In case you do not have the start and end nodes, you must consider all available information to build the network diagram

## Slide 5
P5: Developing the Schedule
Practical Considerations for Developing the Schedule
Extended Network Techniques to Come Close to Reality
Laddering
  Activities are broken into segments (especially long activities) so the following activity can begin sooner and not delay the work.
Lags
  The minimum amount of time a dependent activity must be delayed to begin or end.
  Lags can be used with finish-to-start, start-to-start, finish-to-finish, start-to-finish, or combination relationships.

## Slide 6
P5: Developing the Schedule
Practical Considerations for Developing the Schedule
Extended Network Techniques to Come Close to Reality
Example of Laddering Using Finish-to-Start Relationship

## Slide 7
Practical Considerations for Developing the Schedule
Extended Network Techniques to Come Close to Reality
Example of Laddering Using Finish-to-Start Relationship

## Slide 8
P5: Developing the Schedule
Practical Considerations for Developing the Schedule
Extended Network Techniques to Come Close to Reality
Start-to-Start Relationship

## Slide 9
Practical Considerations for Developing the Schedule
Extended Network Techniques to Come Close to Reality
Finish-to-Finish Relationship
Start-to-Finish Relationship
Combination Relationship

## Slide 10: New Product Development Process
Practical Considerations for Developing the Schedule
Extended Network Techniques to Come Close to Reality

## Slide 11
Practical Considerations for Developing the Schedule
Avoid Dangler Paths
Even if this is not a requirement, it is a good idea because it avoids “dangler” paths. Dangler paths give the impression that the project does not have a clear beginning or ending.
If a project has more than one activity that can begin when the project is to start, or multiple activity at the end ,each path is a dangler path.
Danglers can be avoided by tying dangler activities to a common project start or finish node.

## Slide 12
Practical Considerations for Developing the Schedule
Dummy activities
  Rule: two or more activities cannot share same start and end nodes
  Then, How to represent concurrent activities?
2
3
Lay foundation
Order material
(a) Incorrect precedence relationship
(b) Correct precedence relationship
3
4
2
Dummy
Lay
foundation
Order material
1
2
0

## Slide 13
Practical Considerations for Developing the Schedule
Dummy activities
1
2
3
4
A
D
C
Tasks B and C have the same start and finish nodes
Task D has immediate predecessors of B and C
B
1
2
3
5
C
A dummy task is inserted to preserve the immediate predecessors of D
A new node is inserted to give C a different finish node to B
4
B
A
D

## Slide 14
Practical Considerations for Developing the Schedule
Dummy activities
  Case 2:
Ending node of task B and C, but task C has a precedence ONLY task C
Task D and E have same start and end nodes
  Wrong Diagram

## Slide 15
Practical Considerations for Developing the Schedule
Dummy activities
  Case 2:
  Correct Diagram

## Slide 16
P5: Developing the Schedule
Critical Path Method (CPM):
CPM (or critical path analysis) is a network diagramming technique used to predict total project duration
A critical path for a project is the series of activities that determines the earliest time by which the project can be completed
The critical path is the longest path through the network diagram and has the least amount of slack or float
Slack or float is the amount of time an activity may be delayed without delaying a succeeding activity or the project finish date

## Slide 17
P5: Developing the Schedule
Calculating the Critical Path
First develop a good network diagram
Add the duration estimates for all activities on each path through the network diagram
The longest path is the critical path
Project Time Management
If one or more of the activities on the critical path takes longer than planned, the whole project schedule will slip
unless the project manager takes corrective action

## Slide 18
P5: Developing the Schedule
Calculating the Critical Path
Project Time Management
There can be more than one critical path if the lengths of two or more paths are the same
The critical path can change as the project progresses

## Slide 19
P5: Developing the Schedule
Using Critical Path Analysis to Make Schedule Trade-offs:
Project Time Management
If a task on the critical path is behind schedule, the project manager must be aware of the problem and decide what to do about it.
It is important to know the critical path throughout the life of a project so the product manager can make trade-offs.
Should the schedule be renegotiated with stakeholders?
Should more resources be allocated to other items on the critical path to make up for that time?
Is it acceptable for the project to finish behind schedule?
A technique that can help project managers make schedule trade-offs is determining the free slack for each project activity.

## Slide 20
P5: Developing the Schedule
Using Critical Path Analysis to Make Schedule Trade-offs:
Project Time Management
Free slack (or free float) is the amount of time an activity can be delayed without delaying the early start of any immediately following activities
  Or Is how long an activity can exceed its early finish date without affecting early start dates of any successor(s).
Project managers calculate free slack by doing a forward and backward pass through a network diagram.

## Slide 21
P5: Developing the Schedule
Using Critical Path Analysis to Make Schedule Trade-offs:
Project Time Management
A forward pass through the network diagram determines the early start (ES) and early finish (EF) dates
A backward pass determines the late start (LS) and late finish (LF).
The early start (ES) date is the earliest possible time an activity can start based on the project network logic
The early finish (EF) date is the earliest possible time an activity can finish based on the project network logic.
The late start (LS) date is the latest possible time an activity might begin without delaying the project finish date.
The late finish (LF) date is the latest possible time an activity can be completed without delaying the project finish date.

## Slide 22: Node Configuration
In the nodes, the activity time and the early and late start and finish times are represented in the following manner
ACTIVITY t
ES EF
LS LF
Earliest times are computed as
Earliest finish time = Earliest start time + Expected activity time
EF = ES + t
Earliest start time (ES) = Largest EF of immediate predecessors
1
0
3
3
0
3
Activity duration
Activity number
Earliest start
Latest start
Latest finish
Earliest finish

## Slide 23
P5: Developing the Schedule
At the start of the project we set the time to zero
Thus ES = 0 for both A and B
Start
A t = 2
ES = 0 EF = 0 + 2 = 2
B t = 3
ES = 0 EF = 0 + 3 = 3

## Slide 24
P5: Developing the Schedule
Project Time Management
A 2
0 2
C 2
2 4
H 2
13 15
E 4
4 8
B 3
0 3
D 4
3 7
G 5
8 13
F 3
4 7
Start
Finish
EF = ES + t
ES = Largest EF of immediate predecessors
Forward Pass

## Slide 25
P5: Developing the Schedule
Project Time Management
Latest times are computed as:
Latest start time = Latest finish time – Expected activity time
LS = LF – t
Latest finish time (LF) = Smallest LS of following activities
For activity H
LS = LF – t = 15 – 2 = 13 weeks

## Slide 26
P5: Developing the Schedule
Latest times are computed as:
A 2
0 2
0 2
C 2
2 4
2 4
H 2
13 15
13 15
E 4
4 8
4 8
B 3
0 3
1 4
D 4
3 7
4 8
G 5
8 13
8 13
F 3
4 7
10 13
Start
Finish
LF = Smallest LS of following activities
LS = LF – t
Only 1 following activity
Backward Pass

## Slide 27
P5: Developing the Schedule
Slack Time:
Once ES, LS, EF, and LF have been determined, it is a simple matter to find the amount of slack time that each activity has
Slack = LS – ES, or Slack = LF – EF
 | EARLIEST START, ES | EARLIEST FINISH, EF | LATEST START, LS | LATEST FINISH, LF | SLACK, LS – ES | ON CRITICAL PATH?
A | 0 | 2 | 0 | 2 | 0 | Yes
B | 0 | 3 | 1 | 4 | 1 | No
C | 2 | 4 | 2 | 4 | 0 | Yes
D | 3 | 7 | 4 | 8 | 1 | No
E | 4 | 8 | 4 | 8 | 0 | Yes
F | 4 | 7 | 10 | 13 | 6 | No
G | 8 | 13 | 8 | 13 | 0 | Yes
H | 13 | 15 | 13 | 15 | 0 | Yes
ACTIVITY

## Slide 28
P5: Developing the Schedule
Project Time Management
Slack Time:
From Table, we see activities A, C, E, G, and H have no slack time
These are called critical activities and they are said to be on the critical path
The total project completion time is 15 weeks
Industrial managers call this a boundary timetable
A 2
0 2
0 2
C 2
2 4
2 4
H 2
13 15
13 15
E 4
4 8
4 8
B 3
0 3
1 4
D 4
3 7
4 8
G 5
8 13
8 13
F 3
4 7
10 13
Start
Finish

## Slide 29: Example 2: Earliest Activity Start and Finish Times
1
0
3
3
2
3
5
2
3
3
4
1
5
5
6
1
4
5
8
3
6
6
7
1
7
8
9
1
Start
Design house and obtain financing
Select paint
Lay foundation
Select carpet
Build house
Finish work
Order and receive materials

## Slide 30: Example 2: Latest Activity Start and Finish Times
0
3
1
0
3
3
3
5
2
3
5
2
4
5
3
3
4
1
6
7
5
5
6
1
5
8
4
5
8
3
7
8
6
6
7
1
8
9
7
8
9
1
Start
Design house and obtain financing
Select paint
Lay foundation
Select carpet
Build house
Finish work
Order and receive materials

## Slide 31: Example 2: Activity Slack and Critical Path
* Critical Path: ?
0
9
9
8
8
*7
1
7
8
6
7
6
1
6
7
5
6
5
0
8
8
5
5
*4
1
4
5
3
4
3
0
5
5
3
3
*2
0
3
3
0
0
*1
Slack S
EF
LF
ES
LS
Activity

## Slide 32
Thank you for Listening